## MVP Estimation
Healthcare Management System - MVP API Resource Estimation
Feature | API Resource | Task | Type | Endpoint / Area | Schema Tables (Possibly) | Est. Hours | Status | Notes
Auth and Roles | auth | Patient registration | API + Service | POST /auth/register | users, patient_profiles | 0.5 | Not Started | Hash password, create user, create patient profile shell
| auth | User login | API + Service | POST /auth/login | users, refresh_sessions | 0.5 | Not Started | Validate credentials, block inactive users, issue tokens
| auth | Refresh access token | API + Service | POST /auth/refresh | refresh_sessions, users | 0.5 | Not Started | Validate refresh session and rotate/reissue token
| auth | Logout current session | API + Service | POST /auth/logout | refresh_sessions | 0.5 | Not Started | Revoke refresh session
| auth | Get current authenticated user (by bearer token) | API + Service | GET /auth/me | users, patient_profiles, doctor_profiles, staff_profiles | 0.5 | Not Started | Return role and matching profile summary
| auth | Auth middleware and role guard | Middleware | Protected routes | users | 2 | Not Started | JWT validation plus basic role checks
| auth | Password and token utility services | Service | Auth utilities | users, refresh_sessions | 1.5 | Not Started | Hashing, token signing, token verification
User/Profile Management | users | List users for admin | API + Service | GET /users | users | 0.5 | Not Started | Pagination and role/status filters
| users | Create doctor/staff user (Admin authorized only) | API + Service | POST /users | users, doctor_profiles, staff_profiles | 0.5 | Not Started | Admin creates account and role-specific profile
| users | Update user status (Admin & user authorized only) | API + Service | PATCH /users/{userId}/status | users | 0.5 | Not Started | Activate, deactivate, flag, soft delete
| patients | Get own patient profile | API + Service | GET /patients/me | users, patient_profiles | 0.5 | Not Started | Resolve patient by authenticated user id
| patients | Update own patient profile | API + Service | PATCH /patients/me | patient_profiles | 0.5 | Not Started | Validate demographics and basic medical fields
| patients | View patient details (maybe won't use) | API + Service | GET /patients/{patientId} | patient_profiles, users | 0.5 | Not Started | Doctor/staff/admin access with ownership rules
| doctors | List/search doctors (public) | API + Service | GET /doctors | doctor_profiles, users | 0.5 | Not Started | Specialty filter and active doctor filter
| doctors | View doctor profile (public) | API + Service | GET /doctors/{doctorId} | doctor_profiles, users | 0.5 | Not Started | Public doctor profile details for booking
| doctors | Update own doctor profile | API + Service | PATCH /doctors/me | doctor_profiles | 0.5 | Not Started | Specialty and credentials update
| staff | List staff for admin | API + Service | GET /staff | staff_profiles, users | 0.5 | Not Started | Basic admin staff list
Doctor Discovery | doctors | Calculate available slots (public) | API + Service | GET /doctors/{doctorId}/available-slots | doctor_profiles, appointments, doctor_unavailability | 0.5 | Not Started | Exclude booked appointments and blocked doctor time
Appointment Booking | appointments | Book appointment | API + Service | POST /appointments | appointments, patient_profiles, doctor_profiles, doctor_unavailability | 0.5 | Not Started | Transactional conflict check before create
| appointments | View appointment details | API + Service | GET /appointments/{appointmentId} | appointments, patient_profiles, doctor_profiles | 0.5 | Not Started | Ownership-based visibility
| appointments | Patient appointment list | API + Service | GET /patients/me/appointments | appointments, patient_profiles, doctor_profiles | 0.5 | Not Started | Patient sees own appointments
| appointments | Doctor appointment list | API + Service | GET /doctors/me/appointments | appointments, patient_profiles, doctor_profiles | 0.5 | Not Started | Doctor sees assigned queue
| appointments | Cancel appointment | API + Service | POST /appointments/{appointmentId}/cancel | appointments | 0.5 | Not Started | Store cancellation reason and validate status
| appointments | Mark appointment complete | API + Service | POST /appointments/{appointmentId}/complete | appointments, visits | 0.5 | Not Started | Usually called after visit completion
| doctors | Doctor blocks unavailable time | API + Service | POST /doctors/me/unavailability | doctor_unavailability, doctor_profiles | 0.5 | Not Started | Validate start/end time and ownership
Consultation and Visit Report | visits | Start visit from appointment | API + Service | POST /appointments/{appointmentId}/visit/start | visits, appointments, patient_profiles, doctor_profiles | 0.5 | Not Started | Create one visit per appointment
| visits | View visit details | API + Service | GET /visits/{visitId} | visits, appointments | 0.5 | Not Started | Doctor/admin view, patient limited fields
| visits | Update visit clinical details | API + Service | PATCH /visits/{visitId} | visits | 0.5 | Not Started | Symptoms, diagnoses, notes, prescribed_medicines JSONB
| visits | Complete visit | API + Service | POST /visits/{visitId}/complete | visits, appointments | 0.5 | Not Started | Set end time and update lifecycle
| visits | Patient visit list | API + Service | GET /patients/me/visits | visits, appointments, doctor_profiles | 0.5 | Not Started | Patient sees own visits
| visit-reports | Build visit report read model | Read Model API | GET /visits/{visitId}/report | visits, visit_assigned_tests, test_catalog, lab_order_items, lab_reports, patient_reports, report_attachments | 0.5 | Not Started | Frontend-ready report with medicines and assigned tests
| visit-assigned-tests | Assign tests during visit | API + Service | POST /visits/{visitId}/assigned-tests | visit_assigned_tests, visits, test_catalog | 0.5 | Not Started | Doctor assigns tests; does not create lab order
| visit-assigned-tests | Patient assigned test list | API + Service | GET /patients/me/assigned-tests | visit_assigned_tests, visits, test_catalog | 0.5 | Not Started | Show assigned, ordered_internal, completed, cancelled
Lab Tests | test-catalog | List test catalog | API + Service | GET /test-catalog | test_catalog | 0.5 | Not Started | Search/list available tests
| test-catalog | Create test catalog item | API + Service | POST /test-catalog | test_catalog | 0.5 | Not Started | Admin creates test with default price
| test-catalog | Update test catalog item | API + Service | PATCH /test-catalog/{testId} | test_catalog | 0.5 | Not Started | Admin updates name, category, price
| lab-orders | Order assigned tests at hospital | API + Service | POST /lab-orders | lab_orders, lab_order_items, visit_assigned_tests, patient_profiles | 0.5 | Not Started | Patient selects assigned tests; create order/items
| lab-orders | Patient lab order list | API + Service | GET /patients/me/lab-orders | lab_orders, lab_order_items, test_catalog | 0.5 | Not Started | Patient sees own internal lab orders
| lab-orders | View lab order details | API + Service | GET /lab-orders/{labOrderId} | lab_orders, lab_order_items, test_catalog, lab_reports | 0.5 | Not Started | Ownership and staff/admin access
| lab-order-items | Update lab item status | API + Service | PATCH /lab-order-items/{itemId}/status | lab_order_items, lab_orders, visit_assigned_tests | 0.5 | Not Started | Staff updates requested -> collected -> processing -> completed
| lab-reports | Upload internal lab report | API + Service + Upload | POST /lab-order-items/{itemId}/report | lab_reports, lab_order_items, lab_orders, patient_reports | 0.5 | Not Started | Create internal report and mark assigned test complete
Reports/Documents | patient-reports | Upload external patient report | API + Service + Upload | POST /patients/me/reports | patient_reports, report_attachments, visit_assigned_tests | 0.5 | Not Started | Can link uploaded report to assigned test
| patient-reports | Patient report list | API + Service | GET /patients/me/reports | patient_reports, report_attachments | 0.5 | Not Started | Patient sees own reports
| patient-reports | View patient reports by patient id | API + Service | GET /patients/{patientId}/reports | patient_reports, report_attachments, visits | 0.5 | Not Started | Doctor/staff/admin with access rules
| patient-reports | View report details | API + Service | GET /patient-reports/{reportId} | patient_reports, report_attachments | 0.5 | Not Started | Single report with attachments
| report-attachments | Add report attachment | API + Upload | POST /patient-reports/{reportId}/attachments | report_attachments, patient_reports | 0.5 | Not Started | Validate file metadata/storage key or URL
Billing and Payments | invoices | Create invoice | API + Service | POST /invoices | invoices, patient_profiles, visits | 0.5 | Not Started | Staff/admin creates invoice for patient or visit
| invoices | View invoice details | API + Service | GET /invoices/{invoiceId} | invoices, invoice_items, payments | 0.5 | Not Started | Patient owns invoice; staff/admin can view
| invoices | Patient invoice list | API + Service | GET /patients/me/invoices | invoices, invoice_items, payments | 0.5 | Not Started | Patient sees own billing records
| invoice-items | Add invoice item | API + Service | POST /invoices/{invoiceId}/items | invoice_items, invoices | 0.5 | Not Started | Validate quantity, price, amount
| payments | Record payment | API + Service | POST /invoices/{invoiceId}/payments | payments, invoices | 0.5 | Not Started | Transactional paid/due/status update
| payments | Patient payment history | API + Service | GET /patients/me/payments | payments, invoices | 0.5 | Not Started | Patient sees own payments
Admin Basics | admin-users | Admin user list | API + Service | GET /admin/users | users, patient_profiles, doctor_profiles, staff_profiles | 0.5 | Not Started | Admin dashboard list view
| admin-users | Admin creates doctor/staff user | API + Service | POST /admin/users | users, doctor_profiles, staff_profiles | 0.5 | Not Started | Can reuse user creation service
| admin-users | Admin updates user status | API + Service | PATCH /admin/users/{userId}/status | users | 0.5 | Not Started | Can reuse user status service
| admin-patients | Admin patient list | API + Service | GET /admin/patients | patient_profiles, users | 0.5 | Not Started | Pagination and search
| admin-appointments | Admin appointment list | API + Service | GET /admin/appointments | appointments, patient_profiles, doctor_profiles | 0.5 | Not Started | Date/status filters
| admin-invoices | Admin invoice list | API + Service | GET /admin/invoices | invoices, invoice_items, payments | 0.5 | Not Started | Status/date filters
TOTAL |  | Total estimated backend/API effort |  |  |  | 31.5 |  | Estimate is approximate and should be refined after API contracts
Cross-Cutting | validation | Request validation layer | Validation | DTOs / validators | All write tables | 4 | Not Started | Required fields, enums, dates, numeric constraints
| authorization | Data ownership checks | Security | Policy guards | users plus domain tables | 4 | Not Started | Patient owns own data, doctor sees assigned patients
| errors | Standard API error responses | Infrastructure | Global error filter/handler | N/A | 2 | Not Started | 400, 401, 403, 404, 409, 422 response shape
| pagination | Pagination helpers for list APIs | Infrastructure | List endpoints | List/query tables | 2 | Not Started | page, limit, total, deterministic sort
| testing | Core unit/integration tests | Testing | Test suite | Core MVP tables | 12 | Not Started | Auth, booking conflict, visit report, lab order, payment